## Summary
PLANNING YEAR CHECKLIST: 2018-2019
Summary of Outstanding Items & Assignments
Progress Against Total Checklist
Completed Items |  |  | 0 | 0%
Items in Process |  |  | 0 | 0%
Incomplete Items |  |  | 143 | 100%
Total Items |  |  | 143 | 100%
Project Managers | Board Committee | Board Lead | Committee Members | Categories | Outstanding Items
Academics
Finance
Governance
Marketing
Human Resources
Facility
Legal
Ancillary
Policy
9 Categories
Total Categories
Academics | 14
Finance | 26
Governance | 44
Marketing | 13
Human Resources | 16
Facility | 11
Legal | 10
Ancillary | 5
Policy | 3
TOTAL | 144

## Itemized
2018-2019 Planning Year Calendar
Month | Task | Person(s) Responsible | Board Committee | Progress | Category | Comments
Pre-September | Learning Program
| Identify instructional strategies the school will use to achieve academic goals |  |  | Incomplete | ACADEMIC
| Develop/Revise mission and vision statements for the school |  |  | Incomplete | ACADEMIC
| Compose a brief history of the origin of the school and community need for the school |  |  | Incomplete | MARKETING
| Description of school (grade levels served, expected enrollment demographics, etc.) |  |  | Incomplete | MARKETING
Financial Management/Oversight
| Secure grants |  |  | Incomplete | FINANCE
| Revise and expand the budget in the application to include all secured grants. Develop at least two contingency budgets (one with lowest possible operating enrollment and one other enrollment scenario) |  |  | Incomplete | FINANCE
Governance and Operations
| Determine governance structure |  |  | Incomplete | GOV
| Develop job descriptions for Board of Directors and Officers |  |  | Incomplete | GOV
| Recruit board members with specific expertise (law, finance, education, maketing, real estate, etc.) |  |  | Incomplete | GOV
| Plan and implement board orientation sessions |  |  | Incomplete | GOV
| Criminal background checks conducted for each board member |  |  | Incomplete | LEGAL
| Identify legal status, tax-exempt status (file for 501c3 status) |  |  | Incomplete | LEGAL
Learning Program
| Spend time familiarizing board with the contents and layout of the Department of Instruction website |  |  | Incomplete | ACADEMIC
September | Financial Management/Oversight
| Establish relationship/open account with local banking institution, order checks |  |  | Incomplete | FINANCE
| Designate financial manager for school |  |  | Incomplete | FINANCE
| Identify check writers and signers |  |  | Incomplete | FINANCE
| Decide if the school will take Title I and/or Title II funds |  |  | Incomplete | FINANCE
| Schedule monthly finance committee meetings |  |  | Incomplete | FINANCE
Governance and Operations
| Conduct needs assessment, including evaluating how the site will meet curricular and program needs to advance the mission of the school |  |  | Incomplete | FACILITY
| Identify options and assess accessibility of proposed school locations |  |  | Incomplete | FACILITY
| The board adopts, and each individual signs, a conflict-of-interest policy |  |  | Incomplete | GOV
| Attend Planning Year Session sponsored by the Office of Charter Schools |  |  | Incomplete | GOV
| Establish a board meeting calendar |  |  | Incomplete | GOV
| Review Open Meetings Law |  |  | Incomplete | LEGAL
| Review and print copies of NC General Statute 115C-218 through 115C-218.110 for board members and staff |  |  | Incomplete | LEGAL
| Review civil rights and equity issues (including information produced by the Office for Civil Rights: http://www2.ed.gov/about/offices/list/ocr/index.html) |  |  | Incomplete | LEGAL
| Review bylaws for alignment with Charter School Law and State Board Policies |  |  | Incomplete | POLICY
| Board creates committees for efficient operations |  |  | Incomplete | GOV
| Monthly Board Meeting |  |  | Incomplete | GOV
| Consider hiring a marketing/enrollment coordinator OR identify person responsible for organizing marketing/enrollment activities |  |  | Incomplete | MARKETING
October | Learning Program
| Begin to think about materials and equipment you will need to order to align with your chosen curriculum |  |  | Incomplete | ACADEMICS
Financial Management/Oversight
| Develop internal controls and fiscal policies |  |  | Incomplete | FINANCE
| Acquire forms (purchase orders, etc.) |  |  | Incomplete | FINANCE
Governance and Operations
| Board membership includes individual(s) with legal/policy expertise |  |  | Incomplete | GOV
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Attend Planning Year Session sponsored by the Office of Charter Schools |  |  | Incomplete | GOV
| Submit necessary application/bylaw amendments to the Office of Charter Schools |  |  | Incomplete | POLICY
| Define board committees and write descriptions |  |  | Incomplete | GOV
| Develop job descriptions for director and other start-up staff |  |  | Incomplete | HR
| Develop and begin performing board self-evaluations |  |  | Incomplete | GOV
| Retain legal counsel, where applicable |  |  | Incomplete | LEGAL
| Evaluate/inspect potential sites, enlist facility design help where needed |  |  | Incomplete | FACILITY
| Review local and state building codes/ordinances/regulations |  |  | Incomplete | LEGAL
| Obtain resources for financing a facility |  |  | Incomplete | FACILITY
| Develop a marketing plan |  |  | Incomplete | MARKETING
| Governance Strengthening Exercise |  |  | Incomplete | GOV
| Enrollment projections, caps, and waiting list/lottery plan established |  |  | Incomplete | POLICY
| Monthly Board Meeting |  |  | Incomplete | GOV
| Develop appropriate communications materials (brochures, newsletters) |  |  | Incomplete | MARKETING
| Identify community events at which to market the school |  |  | Incomplete | MARKETING
| Identify strategies to recruit a diverse student body (community groups, etc.) |  |  | Incomplete | MARKETING
Learning Program
| Assign board member to review requirements for students with special needs: https://ec.ncpublicschools.gov/policies/nc-policies-governing-services-for-children-with-disabilities/policies-children-disabilities.pdf |  |  | Incomplete | ACADEMIC
| Create a systematic plan for relationship development with community organizations that have mission alignment with the school |  |  | Incomplete | ACADEMIC
November | Financial Management/Oversight
| Determine first year staffing needs |  |  | Incomplete | HR
| Establish segregation of financial duties (start-up coordinator/director, board, staff) |  |  | Incomplete | FINANCE
Governance and Operations
| Hire start-up coordinator (or school leader) |  |  | Incomplete | HR
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Start-up coordinator/director has clearly defined responsibilities and authority (what can be done without specific board approval) |  |  | Incomplete | GOV
| Attend Planning Year Session sponsored by the Office of Charter Schools |  |  | Incomplete | GOV
| Database of interested/enrolled students is created and utilized to keep track of students/families associated with school during enrollment period |  |  | Incomplete | MARKETING
| Develop a board binder |  |  | Incomplete | GOV
| Board training plan: governance, employment, financial |  |  | Incomplete | GOV
| Necessary facility inspections initiated and required improvements/timeline established |  |  | Incomplete | FACILITY
| Consider how facility supports curriculum and expansion potential |  |  | Incomplete | FACILITY
| Governance Strengthening Exercise |  |  | Incomplete | GOV
| Monthly Board Meeting |  |  | Incomplete | GOV
| Legal counsel reviews lease and any addendums, etc. |  |  | Incomplete | LEGAL
| Site is acquired, lease is signed. |  |  | Incomplete | FACILITY
| Adopt an evaluation process for the director |  |  | Incomplete | GOV
December | Learning Program
| Create a matrix of curriculum resource options to make informed decisions |  |  | Incomplete | ACADEMIC
| Develop curriculum materials purchasing plan |  |  | Incomplete | ACADEMIC
Financial Management/Oversight
| Compare the lease of your proposed site to the rest of your budget |  |  | Incomplete | FINANCE
Governance and Operations
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Attend Planning Year Session sponsored by the Office of Charter Schools |  |  | Incomplete | GOV
| Monthly Board Meeting |  |  | Incomplete | GOV
| Governance Strengthening Exercise |  |  | Incomplete | GOV
| Develop an intake process for students and families |  |  | Incomplete | MARKETING
| Identify strategies to deal with external controversy/internal conflict |  |  | Incomplete | MARKETING
January | Learning Program
| Establish applicant pool for School Director position and staff by recruiting potential candidates through ads placed in multiple media outlets and referrals from charter/education sources. |  |  | Incomplete | HR
Financial Management/Oversight
| If participating in the School Nutrition Program, begin process now. |  |  | Incomplete | FINANCE
Governance and Operations
| Admissions policy and all forms follow NC General Statutes and SBE Policies |  |  | Incomplete | LEGAL
| Monthly Board Meeting |  |  | Incomplete | GOV
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Attend Planning Year Session sponsored by the Office of Charter Schools |  |  | Incomplete | GOV
| Acquire a LEA number |  |  | Incomplete | ANCILLARY
| During enrollment process, develop and utilize a records request form as final verification of enrollment |  |  | Incomplete | MARKETING
| Governance Strengthening Exercise |  |  | Incomplete | GOV
February | Learning Program
| Screen and select potential candidates (multiple candidates identified for Director position and interviewed per hiring policies) |  |  | Incomplete | HR
| Evaluate technology needs and develop a purchase plan |  |  | Incomplete | ACADEMIC
| Create a system for identifying students with special needs |  |  | Incomplete | ACADEMIC
Financial Management/Oversight
| Plan schedule of any renovations that are needed to facility |  |  | Incomplete | FACILITY
Governance and Operations
| Address building security issues |  |  | Incomplete | FACILITY
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Develop hiring procedures for Director and staff (including plan for hiring teachers and staff that reflect the racial/ethnic/cultural character of the school's identified location) |  |  | Incomplete | HR
| Establish staff salary range |  |  | Incomplete | HR
| Design benefit packages for staff |  |  | Incomplete | HR
| Governance Strengthening Exercise |  |  | Incomplete | GOV
| Monthly Board Meeting |  |  | Incomplete | GOV
March | Learning Program
| Determine the profile of teacher candidates desired |  |  | Incomplete | HR
Financial Management/Oversight
| Secure line of credit or establish relationship with lending organization |  |  | Incomplete | FINANCE
| Develop and monitor cash flow plan |  |  | Incomplete | FINANCE
| Complete enrollment report and submit to the Office of Charter Schools |  |  | Incomplete | FINANCE
Governance and Operations
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Monthly Board Meeting |  |  | Incomplete | GOV
April | Learning Program
| Develop specific plan for parent involvement opportunities |  |  | Incomplete | ACADEMIC
Financial Management/Oversight
| Complete enrollment report and submit to the Office of Charter Schools |  |  | Incomplete | FINANCE
Governance and Operations
| Monthly Board Meeting |  |  | Incomplete | GOV
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| If applicable, hire school director and begin transition process for start-up coordinator |  |  | Incomplete | HR
| Director hires or continues hiring licensed staff in conjunction with established hiring policies and school learning program |  |  | Incomplete | HR
| At least two community partnerships initiated |  |  | Incomplete | MARKETING
May | Learning Program
| Identify and hire Special Education Director |  |  | Incomplete | HR
| Identify staff member responsible for Special Education record keeping procedures |  |  | Incomplete | ACADEMIC
Financial Management/Oversight
| Obtain Certificate of Liability Insurance (amounts/types required by Charter Agreement) |  |  | Incomplete | FINANCE
| Complete enrollment report and submit to the Office of Charter Schools |  |  | Incomplete | FINANCE
| Attend Cash Management Training |  |  | Incomplete | FINANCE
| Write regular budget that reflects the projected enrollment and a break-even budget that reflects the minimum number of students the school could open with and still remain financially viable |  |  | Incomplete | FINANCE
Governance and Operations
| Monthly Board Meeting |  |  | Incomplete | GOV
| Work on Ready to Open Progress Report |  |  | Incomplete | GOV
| Ensure charter agreement is signed and submitted to the Office of Charter Schools by the announced deadline |  |  | Incomplete | LEGAL
| Purchase all technology |  |  | Incomplete | ANCILLARY
| Develop a facility contingency plan |  |  | Incomplete | FACILITY
| 75% of staff have been identified for hire |  |  | Incomplete | HR
| 75% of projected enrollment achieved |  |  | Incomplete | MARKETING
June | Learning Program
| Purchase all curriculum materials |  |  | Incomplete | ACADEMIC
Financial Management/Oversight
| Complete the Projected Enrollment input process for School Allotments |  |  | Incomplete | FINANCE
| Notify State Retirement System only if board is participating |  |  | Incomplete | FINANCE
| Notify State Health Plan System only if board is participating |  |  | Incomplete | FINANCE
Governance and Operations
| Monthly Board Meeting |  |  | Incomplete | GOV
| Attend New Charter School Leaders Institute |  |  | Incomplete | GOV
| Install server and other technology equipment |  |  | Incomplete | ANCILLARY
July | Learning Program
| Staff assignments adjusted based on enrollment projections |  |  | Incomplete | ACADEMIC
| Staff professional development planned and implemented |  |  | Incomplete | ACADEMIC
| At least 50% of teachers are properly licensed |  |  | Incomplete | HR
| Submit "LEA/Charter Completion of ACT EDDIE Updates" to RAC |  |  | Incomplete | ANCILLARY
Financial Management/Oversight
| Budget evaluated against enrollment projections; revised if necessary |  |  | Incomplete | FINANCE
| Complete enrollment report and submit to the Office of Charter Schools |  |  | Incomplete | FINANCE
| Submit "Number of Students Below the Poverty Threshold" form to School Allotments |  |  | Incomplete | FINANCE
Governance and Operations
| Make necessary repairs/installations per lease |  |  | Incomplete | FACILITY
| Monthly Board Meeting |  |  | Incomplete | GOV
| Arrange for custodian/maintenance services |  |  | Incomplete | ANCILLARY
| Ongoing staff development program designed, approved, and communicated to teachers/staff |  |  | Incomplete | HR
| Conduct criminal background/reference checks of all staff |  |  | Incomplete | HR
Note on E3: kwilliams: Insert Complete, Incomplete, or In Process