## Sheet1
Ready to Open Progress Report & Evidence Checklist
The highlighted items are due December 3, 2018.
| Description | Rating Criteria | Criteria Self-Evaluation: Paint Red or Green (Completed by School) | If a section is not complete, please provide an explanation and timeline to completion. The ending point of the timeline should be no later than January 4, 2019. At that time, evidences of completion are due to OCS.
Governing Board | Board Meeting Minutes from August 2018 to November 2018. | Evidence of regular board meetings and minutes indicating the understanding of key laws (e.g., Open Meetings Law) and use of best practices.
| The board formally adopted a school calendar representing the academic year that meets the requirements specified in charter school law. | Evidence has been provided that the requirement has been met.
| Board Bylaws | Bylaws have been formally approved by the local board and OCS has a new clean electronic copy of the document.
| Evaluation Tools | Evaluation tools for the school’s executive (principal/director) and governing (board) entities
| Board List | Current board member list and contact information is provided to OCS.
Student Accountability Plans | Testing/accountability coordinator job description | Evidence has been provided that the requirement has been met.
| Develop draft of testing calendar | Evidence has been provided that the requirement has been met.
| Policy in place regarding student enrollment (10/20-day rule) in End of Course (EOC) classes | Evidence has been provided that the requirement has been met (if applicable).
Key Staff | Official employee agreement is formally approved by the board | Evidence has been provided that the requirement has been met.
School Safety | Policies are adopted and meet the requirements under § 115C-218.75(a). | Evidence has been provided that the requirement has been met.
Policies | Instructional Programming: (1) Structure of School Calendar; (2) Structure/Length of School Day | At a minimum, these 2 policies must be developed and formally adopted by the board.
| Operations: (1) Criminal Background Checks for Staff; (2) Criminal Background Checks for Volunteers; (3) Admissions; (4) Lottery (Policy & Application); (5) Records Retention | At a minimum, these 5 policies must be developed and formally adopted by the board. Note also that the Lottery Application is to be submitted in addition to the Lottery Policy.
| Governance: (1) Board Committees; (2) Conflict of Interest (see G.S. 115C-218.15), (3) Nepotism (see G.S. 115C-218.15); (4) Third-party Agreements (including parent organizations); (5) Grievance for Staff; (6) Grievance for Families; (7) Employee Agreements; (8) Board Member Residency; (9) Board Meeting Calendar | At a minimum, these 9 policies must be developed and formally adopted by the board.
| Finances: (1) Budget Approval; (2) Third-party Contracts; (3) Access to Funding; (4) Audits; (5) Purchasing; (6) Federal Funds | At a minimum, these 6 policies must be developed and formally adopted by the board.
Handbooks | Employee Handbook (including policies related to hiring and firing of staff) | Handbook is complete and has been approved by the board.

## Sheet2
Self-Evaluation
Met
Not Met