## Slide 1: Office Of Civil Rights Data Collection (OCR / CRDC)
State Level Submission Project Status Update
June 19, 2015
Terra Dominguez
State OCR Coordinator
terra.dominguez@dpi.nc.gov

## Slide 2: High Level Info
OCR – Office of Civil Rights
CRDC – Civil Rights Data Collection
National Data Collection
Collected every two years
Previous year data
Originally Presented: 10/21/2014

## Slide 3: Federal Submission Dates
Submission begins Feb 2015
75 business days to complete submission
We hope to be done much sooner 
Originally Presented: 10/21/2014
Updated: 12/2/2014, 1/20/2015

## Slide 4: Communications
All communications are sent to staff designated as the ‘OCR Coordinator’.
All communications are then sent via the NC SIS distribution list.
Please make every effort to route OCR notifications to the appropriate staff.
Originally Presented: 10/21/2014

## Slide 5: About this Presentation
This presentation is a collection of each status update.
The presentation may be downloaded in full at: http://www.nc-sis.org/course_list.html
Slides from previous updates/webinars have been hidden to allow attendees to focus on current information.
Originally Presented: 11/4/2014

## Slide 6: About this Presentation…
Slides that are hidden will print if your print settings are not updated.
If you are using this presentation to follow along with the Status update, the following is recommend:
  Click File
  Click Print
  From Settings, click the Print All Slides drop-down
  Uncheck Print Hidden Slides
Originally Presented: 11/4/2014

## Slide 7: About this Presentation…
To use hidden slides for re-delivery :
  Download and open the original PowerPoint file
  From the left pane, right click slide
  Click ‘Hide Slide’
Originally Presented: 11/4/2014

## Slide 8: Updates to Formatting
November 4:
  Page numbers
    Page numbers do not update if a slide is hidden
  ‘Originally Presented’ date
  Latest ‘Known Issues’ stamped with
December 2:
  Slides may be re-ordered
  ‘Updated’ date added to original date of slide
  ‘Known Issues’ that are resolved stamped with
Originally Presented: 10/21/2014
Updated: 12/2/2014

## Slide 9: Project Tasks
Evaluate SY 13/14 requirements for CRDC
Build CRDC specific screens
Load all student data into PowerSchool
Develop PowerSchool CRDC report logic
Create state level submission files (inclusive of all data requested)
Participate in Federal pilot project
Submit data to the OCR
Review data in Federal tool (LEA level task)
Correct any erroneous data (Collaborative task)
  Re-submit (if needed)
Approve Federal Submission (LEA level task)
Originally Presented: 10/21/2014

## Slide 10: Task 1 & 2 - Complete
Engagement with OCR, Pearson and SAS development/support staff
Screen was updated in to SY 13/14 Federal Requirements in July
LEAs / Charters should have LEA and School Level forms complete
  IMPORTANT – verify all questions have been answered. If leading questions are blank / NULL, any subsequent question will report as ‘No’
Originally Presented: 10/21/2014

## Slide 11: Example
Originally Presented: 10/21/2014

## Slide 12: Exclude from CRDC Report (<300 schools)
Include if:
  PK center (location)
  Private school student receiving services (location)
  Student is receiving services but does not attend a public school
Originally Presented: 10/21/2014

## Slide 13: Exclude from CRDC Report (<300 schools)…
Exclude if:
  Used for grouping; student ADM is associated to another school
  Used for assignment / evaluation
  FTE School
  Unused ‘program’ schools
Originally Presented: 10/21/2014

## Slide 14: More Info on Program & <300 Schools
Each LEA is using the NC DPI Program Schools differently and has the opportunity to create schools numbered below 300 in PowerSchool for their own local use.
The NC DPI wants students receiving services included in the OCR counts.
Previously this data was reported in the ‘000’ school. The NC DPI will work with the OCR on how / where the data should be reported. This is a pending item.
Originally Presented: 10/21/2014

## Slide 15: One More Thing On <300 Schools…
Schools <300 are not connected to the Education Directory & Demographic Information Exchange (EDDIE)
LEAs / Charters must complete the School Information screen in PowerSchool for each school created at the local level to the fullest extent possible.
If you have questions, issues or concerns please contact the Support Center.
Originally Presented: 10/21/2014

## Slide 16: Tasks 3, 4 & 5 - in Progress
3rd Party users
  Have been notified and provided import procedures and due dates
Data loaded by the NC DPI in November:
  LEP
  SAT / ACT
  AP Exams
Section 504 – let’s talk..
Originally Presented: 10/21/2014

## Slide 17: Section 504 Records in PowerSchool
Data due by LEAs October 17, 2014
CRDC is not reporting on accommodations
Can be added to withdrawn/transferred and graduated student records
Section 504 designation is a local policy
  Records in PowerSchool should reflect the start and end dates of the Section 504 designation/plan within your LEA.
Originally Presented: 10/21/2014

## Slide 18: Section 504 Records in PowerSchool…
Section 504 designation is a local policy
  Records in PowerSchool should reflect the start and end dates of the Section 504 designation/plan within your LEA.
  End dates are not required unless:
    Student’s plan ends
    Student is no longer eligible for Section 504
Originally Presented: 10/21/2014

## Slide 19: Section 504 Records in PowerSchool…
Entry Date must be on or before Oct. 1, 2013 to be included in the CRDC
Scenario (Section 504 record) | On CRDC SY 13/14?
Entry Date = 9/17/07, Exit Date = null | Yes
Entry Date = 10/01/13, Exit Date = null | Yes
Entry Date = 10/01/13, Exit Date = 7/14/14 | Yes
Entry Date = 9/17/07, Exit Date = 9/29/13 | No
Originally Presented: 10/21/2014

## Slide 20: CRDC Reports in PowerSchool
Still in Development
Must be run at the LEA level
  Run in SY 14/15
Do not have Exceptions
Will not need Approval
School level reports include detail views:
  Students
  Courses
Submission End Date in PowerSchool is will be updated
Originally Presented: 10/21/2014

## Slide 21: CRDC Report Known Issues
Scenario | Action/ Resolve
Incorrect Grade Levels CRDC Reports are showing incorrect grade levels. For example: A middle school with PK students reports as having PK-8 and SY 13/14 EDDIE data is accurate. | Resolve: November Maint Wknd Action: Contact the Support Center if your SY 13/14 EDDIE grade levels are not accurate.
IB Program Indicator Reporting courses based on 4th Character | Resolve: November Maint. Wknd
Low / no course enrollment counts | Resolved: November Maint. Wknd
Red Dot of Death | Action: <300 School: terms – are they missing SY 13/14? Do you need it? No = exclude from CRDC New school: terms – are they missing SY 13/14? Yes = exclude from CRDC ( they weren’t there in SY 13/14)
Originally Presented: 10/21/2014

## Slide 22: State Submission Files
State level files are in development in parallel with tasks 3 and 4
First iteration due Oct 17, 2014
Includes data from other systems as requested by the OCR
Originally Presented: 10/21/2014

## Slide 23: The ‘Other’ Data
Originally Presented: 10/21/2014

## Slide 24: Tasks 6 & 7
The NC DPI will participate in the federal pilot
Pilot scheduled to begin week of Oct 20, 2014
Once CRDC reports are complete, LEAs will be notified to run the reports and review the data
  LEAs are welcome to run the report prior
LEAs will be notified of the NC DPI federal submission date
Originally Presented: 10/21/2014

## Slide 25: Tasks 8, 9 & 10 - Pending
As Federal/State/Local processes becomes solidified, notifications will be sent to OCR Coordinators and NC SIS Coordinators regarding:
  Access to Federal Tool
  Correction methods
  Approval Process
Originally Presented: 10/21/2014

## Slide 26: November 4th Agenda
November 4th Status Updates
Review of Known Issues / Recent Fixes
November 14th PowerSchool Maint. Weekend
Reviewing CRDC PowerSchool Data
‘What If’s and Reminders
Originally Presented: 11/4/2014

## Slide 27: November 4th Status – Complete
LEAs should have completed:
  LEA and School level CRDC PowerSchool Screens
    Communication sent 9/22/2014 by Terra Dominguez / NC SIS
  SY 13/14 Section 504 records in PowerSchool
    Communication sent 9/30/2014 by Terra Dominguez / NC SIS
    QRD located: http://www.nc-sis.org/student_information.html
  Updates to Incident data (Zero Tolerance)
    Communication sent by10/6/2014 by Ken Gattis / NC SIS / Terra Dominguez
Originally Presented: 11/4/2014

## Slide 28: November 4th Status – In Progress
Limited English Proficient (LEP)
  50% complete
SAT / ACT / AP exam scores
  25% complete
3rd party data loads (specific LEAs)
  Pending templates from DPI
Originally Presented: 11/4/2014

## Slide 29: November 4th Status – In Progress
State level submission file
  25 % complete
  First iteration of submission file delivered for review
    The NC DPI is working with current existing data for testing
    Testing in Federal tool - pending
    First ‘true submission’ date - pending
LEAs will receive notification prior to first ‘true submission’ to allow final check of PowerSchool data
Originally Presented: 11/4/2014

## Slide 30: November 4th Status- Pending
LEA submission validation process
  State level Federal OCR webinar Nov 5th
    Update on Federal submission window dates
    Details of pilot phase expected
    Information on Federal tool security anticipated
Originally Presented: 11/4/2014

## Slide 31: PowerSchool Maint. Weekend – November 14th
Most fixes will be implemented during the November 14th PowerSchool Maintenance weekend.
OCR Coordinators should begin to examine their data carefully after these updates.
Please report all issues through the Home Base Support Center as soon as possible.
If unable to create a Remedy ticket, please contact Terra Dominguez at: terra.dominguez@dpi.nc.gov
Originally Presented: 11/4/2014

## Slide 32: Reviewing CRDC PowerSchool Data
OCR Coordinators should have access to view all schools within the LEA/Charter
  CECAS, Migrant, Homeless, DPI FTE School
  Contact the PowerSchool Coordinator for appropriate access
LEA Level CRDC Reports are a collection of all schools that have not been Excluded from the CRDC reports
  Review slides 11-14 for information on Excluding Schools <300 from the CRDC reports
Originally Presented: 11/4/2014

## Slide 33: Reviewing CRDC PowerSchool Data…
PowerSchool CRDC Data Views have been formatted based on Part 1 and Part 2 of the Federal website’s OCR / CRDC documentation.
http://www2.ed.gov/about/offices/list/ocr/data.html
  2013-2014 LEA Form
  2013-2014 School Form
LEA CRDC
School CRDC
Originally Presented: 11/4/2014

## Slide 34: Reviewing CRDC PowerSchool Data…
CRDC reports contain filters within the interface
  Filters align with Categories (columns displayed within the interface)
  Categories align with the OCR / CRDC documentation
CRDC reports can be exported to Excel
  Allows filtering from Excel for quick review
  User can navigate system to review settings, student records without losing CRDC output
Originally Presented: 11/4/2014

## Slide 35: Reviewing CRDC PowerSchool Data…
Originally Presented: 11/4/2014

## Slide 36: Reviewing CRDC PowerSchool Data…
School Level Reports have two additional views that allow staff to verify aggregate counts
  Student Detail by School (Part 1 & Part 2)
    List of all students enrolled as of October 1, 2013 and their indicators
  Student Class Detail by School (Part 1 only)
    List of all classes as applicable to the CRDC as of October 1, 2013
Originally Presented: 11/4/2014

## Slide 37: December 2nd – Agenda
Status Update
Known Issues / Resolved Items
PowerSchool Dec 12 Maintenance Weekend
NC Public Schools OCR Website
Next Steps
Originally Presented: 12/2/2014

## Slide 38: December 2nd Status - Complete
LEA and School Screen Data Entry
Section 504 records for SY 13/14
Zero Tolerance updates for SY 13/14 records
LEP data loads
  SY 13/14 LEP data is visible on CRDC reports only
Originally Presented: 12/2/2014

## Slide 39: December 2nd Status – In Progress
SAT, ACT and AP Exam scores
3rd Party data from select LEAs
PowerSchool CRDC reports
Federal Submission pilot
Originally Presented: 12/2/2014

## Slide 40: December 2nd Status - Pending
Completion of PowerSchool CRDC reports
Notification of collection dates from OCR
LEA demonstration of Federal CRDC tool
Logins and security process
Process for reporting issues in the CRDC tool
Originally Presented: 12/2/2014

## Slide 41: December 4th – NC Public OCR Website
Federal OCR Report Requirements Documents
Status Webinar link, recording's, presentation
OCR LEA / Charter Contacts
Archived Notifications
http://www.ncpublicschools.org/data/management/ocr/
Originally Presented: 12/2/2014

## Slide 43: Who Should be an OCR Contact?
OCR Contacts will be the first staff members who are provided access to the Federal CRDC tool
Staff member who will approve the federal submission (business owner)
Staff member who will support collection process (technical or other staff)
Originally Presented: 12/2/2014

## Slide 44: December 4th - Next Steps - LEAs
Review LEA and Charter Contact information
  Provide the 10 elements requested on the website
  Remedy ticket – Subject: CRDC Contact List
    One ticket per LEA/Charter please
    Identify technical contact
    Identify staff who will approve submission
http://www.ncpublicschools.org/data/management/ocr/
Verify grade levels in all schools using EDDIE
  Remedy ticket – Subject: CRDC Grade Levels
    One ticket per LEA/Charter please
Originally Presented: 12/2/2014

## Slide 45: January 6th - Agenda
Happy New Year!
Status Update
Known / Resolved Issues
NC DPI Courses for OCR
Adding CRDC Reports to Schools
Next Steps
Originally Presented: 1/6/2015

## Slide 46: January 6th – Status - Complete
LEA and School Screen Data Entry
Section 504 records for SY 13/14
Zero Tolerance updates for SY 13/14 records
LEP data loads
  SY 13/14 LEP data is visible on CRDC reports only
SAT, ACT and AP Exam Scores
    SY 13/14 data is visible on CRDC reports only
Originally Presented: 1/6/2015

## Slide 47: January 6th – In Progress
3rd Party data from select LEAs
PowerSchool CRDC Reports
Federal Submission Pilot
OCR Coordinators Contact List
Originally Presented: 1/6/2015

## Slide 48: January 6th – Status - Pending
Completion of PowerSchool CRDC reports
Notification of Collection Dates from OCR
Demonstration of Federal CRDC tool
Login and Security Process
Process for Reporting / Correcting Data Issues in Federal CRDC tool
Originally Presented: 1/6/2015

## Slide 49: NC DPI Courses for OCR
OCR Course | NC DPI Course Code (SY 2013-14)
Algebra I | 2100, 2101, 2102, 9320, 9321, 2103, 2104, 2105, 2106, 2107, 2108
Geometry | 2200, IX65, 2201, 2202
Algebra II | 2300, 2301, 2302
Advanced Math | 2400, 2401, 2402, 2403, 2404, 2405, 2407, 2500
Science | 3320, 3321, 3370, 9232, 9332, 9333, 3420, 3421, 3430, 3431
AP Math | Courses where first character is' 2' and fifth character is '7'
AP Science | Courses where first character is' 3' and fifth character is '7'
AP ‘Other’ | Courses where first character is not '2' or '3' and fifth character is '7'
IB Courses | No courses that begin with Alpha Char,6,7,8 and fifth character is '8' and student is in grades 9-12
Originally Presented: 1/6/2015

## Slide 50: Adding CRDC Reports to Schools
Does not replace other required report settings
Specific to year
Can be used for any report in State Dashboards
Can be set at LEA or School level
If a school is not set to Display, does not impact LEA reports
Home Base Bulletin - 12/19/14
Originally Presented: 1/6/2015

## Slide 51: Adding CRDC Reports – LEA Level
From LEA Office, navigate to State Reports.
Click the Details icon for selected report.
Click Show/Hide Collection From Schools.
Make the appropriate selection from the Display in Dashboard? drop-down for the applicable school(s).
Click Submit.
Originally Presented: 1/6/2015

## Slide 52: PowerSchool CRDC Report Reminders
Run CRDC reports in the current year (Term 14-15)
Re-run reports each time there is an update to
  Report logic
  Student data
  Course data
  CRDC screens
Originally Presented: 11/4/2014

## Slide 53: PowerSchool CRDC Report – ‘What If…’
Originally Presented: 11/4/2014
‘What If…’ | Do this …
I want to see if my schools have completed the CRDC screens in PowerSchool? | Determine how many schools should be reporting View CRDC School Detail – Part 1 Filter or export and filter by school to peruse through the school level CRDC screen questions
My ‘Overall Student Enrollment’ (CRDC Student Aggregations by School- Part 1) looks wrong? I know I had ‘X’ number of students at the end of the year. | Was your student enrolled as of October 1, 2013? Students who were not enrolled on the snapshot date of October 1, 2013 will not be reported for the SY 13/14 CRDC.
I know my school had more classes than what is reported on the CRDC? | Was the class in second semester? Classes are counted as of October 1, 2013, unless the LEA schedules block courses. Second semester classes are not reported for the SY 13/14 CRDC.
My grade levels are reporting incorrectly? I see PK through 8th grade. I have PK and 6-8th grade only. | Are your SY 13/14 grade levels in EDDIE correct? Yes – Hold tight for the PowerSchool Nov Maint. weekend No – Submit a Support Ticket immediately

## Slide 54: Adding CRDC Reports to Schools
Does not replace other required report settings
Specific to year
Can be used for any report in State Dashboards
Can be set at LEA or School level
If a school is not set to Display, does not impact LEA reports
Home Base Bulletin - 12/19/14
Originally Presented: 1/6/2015

## Slide 55: Next Steps
Review / Verify Contacts
January 20th – Demo of the Federal OCR Portal
Please continue to report PowerSchool issues!
Originally Presented: 1/6/2015

## Slide 56: January 20th - Agenda
OCR Federal Portal Demo
Status Update
Known / Resolved Issues
EC Data
Correcting Previous Year Grade Levels
Next Steps
Originally Presented: 1/20/2015

## Slide 57: 2013-14 Civil Rights Data Collection (CRDC) Portal Demo
Abby Potts Research Analyst
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 58: What is different this year?
NEW opportunity for State Education Agencies (SEAs) to pre-populate CRDC forms with already collected data.
Redesign of the web tool with intuitive navigation and resources to accurately respond to questions.
Ability to grant permissions to schools, others in the district, or the state to upload or enter data.
New tools to view and respond to errors and warnings.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 59: What Federal Resources are Available now?
Find survey materials, excel templates, tip sheets, and lists of data elements to prepare for the 2013-14 and 2015-16 CRDC
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 60: Resources
U.S. ED documentation is located: http://www2.ed.gov/about/offices/list/ocr/data.html. Download the “2013-14 Table Layouts with Definitions”
    2013-2014 LEA Form
    2013-2014 School Form
      Full set of CRDC school-level questions for all schools and justice facilities, including high schools, and school with the highest grade no higher than 8 that offer Algebra I or Geometry
    2013-2014 Elementary School Form
      Only for schools with the highest grade not greater than 6
    2013-2014 Elementary/Middle School Form
      Only for schools with the highest grade not greater than 8 that do not offer Algebra I or Geometry
CRDC.GRADS360.org
Originally Presented: 10/21/2014,
Updated 1/20/15

## Slide 61
Learn about the CRDC including background information, FAQs, etc.
Opening and due date information.
New users starter kit.
Recently posted or updated documents
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 62
Select view all to access excel templates
School expenditure tips
Vendor letter
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 63: 2013-14 CRDC Schedule
Timeline & What to Expect for the Upcoming Data Submissions
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 64: What should you expect for this CRDC?
Phase I: Contact & Directory
Identify a Primary Point of Contact for each school district
Phase II: Data Collection
Phase III: Data Reporting
Submission System Opens
Confirm the list of schools required to report CRDC data (e.g., schools serving students for at least 50% of the day).
School districts collect CRDC data over the course of the school year.
NC will submit data and Districts can certify their CRDC data to the U.S. Department of Education
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 65: Frequently Asked Questions
When will the new system open for school districts to submit data?
  The new CRDC system will open in February 2015.
What is the due date for the 2013-14 CRDC?
  LEAs will have at least 75 days to complete their data submissions after the system opens. Any delay in the opening date will also push back the due date for the CRDC.
Why is the opening delayed?
  OCR and NCES needed additional time to test the system to ensure it works as intended for all types of school districts. Additionally, some school districts participating in a pilot of the new tool provided excellent ideas on ways to improve the system. We are working to incoporate those ideas to improve the experience for all LEAs.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 66: How Usernames will be delivered?
Look for an email notification from the CRDC system asking you to confirm your email address. (Check spam filters)
Click on the link to confirm your email address. You then will be prompted to create a password.
Following verification of your account you will have immediate access to the CRDC system, and a confirmation email will be sent to you. Use your email and password for ongoing access to the system.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 67: What does the new Federal tool look like?
2013-14 CRDC Submission System
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 68: Home Screen
New unique username & password for each users. Not the same as AWS username and password
Originally Presented: 1/20/2015, compliments of the OCR
Notes: Previously the LEA username was the LEA ID.

## Slide 69
Comprehensive collection of all resources
Add new users & manage permissions
Error & data reports
Viewable for ED, SEA, and some charter schools
Updates and messages posted at the top of the screen.
Select csv file for upload
Review tables
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 70: ADMIN: New for 2013-14
Allow access to certain sets of questions on the CRDC to offices or school staff.
Designed for mid-sized to larger school districts
Examples Cases
  Enable or Disable SEA access to CRDC forms
  Provide the high school athletics director access to the interscholastic athletics data entry tables
  Human Resource Office will be able to upload flat files with FTE counts directly into the system to pre-populate forms.
  Pre-populate forms with data provided by SEAs
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 71: ADMIN
Step #1: Add new users to the CRDC
Step #2: Grant school-level or LEA-level permissions
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 72: ADMIN
Add new users
Manage access to CRDC modules & schools
Remove users
NC LEAs will see NCDPI already has access to the CRDC site to pre-populate data
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 73: ADMIN
Manage permissions by school and/or by CRDC module
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 74: Data Web Screens
Data entry screens, error reports, and onscreen tips
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 75: School Screens
New ability to navigate by school or by question.
Set sort order for schools.
Hide optional questions
Originally Presented: 1/20/2015, compliments of the OCR
Notes: For SEAs providing some, but not all of the CRDC data

## Slide 76: School Status Page
View errors and warnings in submission.
Status of data entry: Date last modified and percent complete. Indication of whether the NC DPI has uploaded data.
Navigate by “data modules”
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 77: Module Landing Page
CRDC questions or tables. Information in parenthesis links back to the OCR survey form.
Originally Presented: 1/20/2015, compliments of the OCR
General instructions.

## Slide 78: Data Screen
Switch between school mode and table mode navigation.
Review errors and warnings for this table.
Expandable Q&A’s specific to this question.
“Data request”
Auto-totals by race, gender, and grand total.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 79: On-screen Warnings & Errors
Warnings and errors will appear on the data entry screens.
Some errors can be resolved by a comment – triggering when plausible, but rare, scenarios occur.
For example, in an LEA with high student mobility, a fall enrollment count of 1 American Indian student is reported but 14 American Indian students chronically absent over the year. To resolve the error, select a reason code.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 80: Data reports
Downloadable Excel Files of Entered or Uploaded Data
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 81
Download a file of all data entered into the system (can also be re-uploaded).
Error report with list of warnings/errors. LEAs can provide comments, make changes to data, and re-upload the file to make corrections.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 82: Additional Resources
Tip Sheets, FAQs, etc.
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 83: Resources
Originally Presented: 1/20/2015, compliments of the OCR

## Slide 84: January 20th – Status - Complete
LEA and School Screen Data Entry
Section 504 records for SY 13/14
Zero Tolerance updates for SY 13/14 records
LEP data loads
  SY 13/14 LEP data is visible on CRDC reports only
SAT, ACT and AP Exam Scores
    SY 13/14 data is visible on CRDC reports only
Originally Presented: 1/20/2015

## Slide 85: January 20th – In Progress
3rd Party data from select LEAs
PowerSchool CRDC Reports
OCR Coordinators Contact List
EC Data Verification and Upload
Grade Level Correction Enhancement
LEA Action Needed: Exclude Graduated Schools
Originally Presented: 1/20/2015

## Slide 86: January 20th – Status - Pending
Completion of PowerSchool CRDC reports -February PowerSchool maintenance weekend
Notification of Collection Dates from OCR
Federal Portal Access
Process for Reporting / Correcting Data for the CRDC
Originally Presented: 1/20/2015

## Slide 87: January 6nd Known Issues Update
Scenario | Resolve / Action
EC Data – reports are currently picking up any student with indicator, in any year. | Pending: February Maint. Wknd
Retentions (1) – indicator reports incorrectly | Pending: February Maint. Wknd Issue – bug – 4th grade indicator only
Retentions (2) – counts appear incorrect | Resolved: requires more research – appears to be a non issue – please report NOW if you suspect your retentions are incorrect.
AIG – Services reported at wrong school | Resolved: Process issue, report functioning as designed
Originally Presented: 1/6/2015,
Updated 1//20/2015

## Slide 88: December 2nd Known Issues Update
Scenario | Resolve / Action
Block Courses are not counted | Pending: December February Maint. Wknd
Grade 13 is not included | Resolved : December Maint. Wknd
Justice Facility Hours appear randomly | Resolved : December Maint. Wknd
AP Special Courses indicator | Resolved : December Maint. Wknd
Originally Presented: 12/2/2014,
Updated 1/6/2015, 1/20/2015

## Slide 89: November 4th Known Issues Update
Scenario | Resolve / Action
School Level – Section 504 - ability to update data outside of user’s school School users had the ability to update records of students who had transferred if accessing from the Special Program Enrollment View screen. | Resolved as of October 24th School users still have the ability to create a list of Section 504 students and LEA Coordinators still have access to the Special Program Enrollment View screen. Communicated via NC SIS 10/29/2014
LEA Level - CRDC School Detail – Part 1 reports all data as ‘No’ | Resolved as of November 3rd
Submission End Date for CRDC Reports | Resolved: November Maint. Wknd Update to November 30th (may be re-evaluated)
Section 504 data is not reporting | Resolved: November Maint. Wknd Logic to be updated with ‘contains 504’ statement
Approval Button for CRDC Reports | Resolved: November Maint. Wknd
Unable to see Dashboard in ‘Non-State Reporting’ schools | Resolved: December Maint. Wknd 12/19/2014 Home Base Bulletin
Originally Presented: 11/4/2014
Updated 12/2/2014, 1/6/2015

## Slide 90: CRDC Report Known Issues
Scenario | Action/ Resolve
Incorrect Grade Levels CRDC Reports are showing incorrect grade levels. For example: A middle school with PK students reports as having PK-8 and SY 13/14 EDDIE data is accurate. | Resolved: November Maint Wknd Contact the Support Center if your SY 13/14 EDDIE grade levels are not accurate. Enhancement in February that will allow LEAs to make corrections.
IB Program Indicator Reporting courses based on 4th Character | Resolved: November Maint Wknd
Low / no course enrollment counts | Resolved: November Maint Wknd
Red Dot of Death | Action: <300 School: terms – are they missing SY 13/14? Do you need it? No = exclude from CRDC New school: terms – are they missing SY 13/14? Yes = exclude from CRDC ( they weren’t there in SY 13/14)
Originally Presented: 10/21/2014, Updated 12/2/2014. 1/20/2015

## Slide 91: Update - EC Data Load
EC Data from PS will not consistently report SY 13/14 student EC records
  EC Data from PS is based on a student’s current EC information (CECAS, 3rd Party)
DPI will load EC data using the December 2013 Head Count(SY 13/14)
Data will only be visible from the CRDC reports
91
Originally Presented: 1/20/2015

## Slide 92: Previous Year Grade Level Correction PowerSchool Screen
Previous year grade level feed from EDDIE has been stopped in PS Production
Update access for LEA Level staff
Read Only after CRDC is complete
Locate Year ID 2300
Using EDDIE codes, type grade levels, separate grade levels with a colon ( : )
Click Submit
    Example: KG:06:07:08
92
Originally Presented: 1/20/2015

## Slide 93: Next Steps
Review Contact List sent 1/20/2015
Exclude the PowerSchool Graduated School from CRDC
All LEAs and Charters should run the CRDC reports (at the LEA level) the week of Monday, February 9, 2015

## Slide 94: OCR / CRDC Status Webinars
October 21
  1pm-2:30
November 4
  1pm-2:30
November 18
  1pm-2:30
December 2, 2014
  1pm-2:30
December 16, 2014
  1pm - 2:30
January 6, 2015 –
  1pm-2:30
January 20, 2015 –
  1pm-2:30
Originally Presented: 10/21/2014, Updated 12/2/2014, 1/5/2015
OCR Status Updates will resume in March
New registration link pending

## Slide 95: OCR Symposium Sessions
Symposium (Subject to Change)
  Monday, February 23, 2015
  Tuesday, February 24, 2015
  Looking forward to seeing you at the Home Base Symposium!

## Slide 96: March 15th - Agenda
PowerSchool CRDC Report Status
Federal Submission Portal
  Submission Window
  Access
  Provisioning Accounts
  Familiarize Yourself with the Tool – Resources
State Data Load Status and Load Schedule
  LEA / Charter Responsibilities
  Errors, Warnings and EDFacts
Support and Resources

## Slide 97: PowerSchool CRDC Report Status
100% of PowerSchool CRDC LEA level reports were run by all LEAs and charter schools
99.1% were re-run during the week of April 13, 2015
  Why was this important? Final updates to report logic were made the weekend prior, requiring the need to re-run for the latest changes
PowerSchool Report Views were lost during the first week of May
All LEA level PowerSchool reports have been restored
Originally Presented: 5/15/2015

## Slide 98: Federal Portal – Submission Window
The OCR due date has not been determined
Due date will be posted in the NOTIFICATIONS BOX on the Submission Tool
Due date will also be posted on Grads 360
Grads 360 link for CRDC: https://crdc.grads360.org
The NC DPI will send notification to OCR Coordinators
Originally Presented: 5/15/2015

## Slide 99: Federal Portal - Accounts
The OCR sent accounts to LEA staff April 16, 2015
Check your SPAM and Junk mail
If you did not receive an account, contact CRDC Partner Support at:
(844) 338-2732 or CRDC@SANAMETRIX.COM
Originally Presented: 5/15/2015

## Slide 100: Federal Portal – Provisioning Accounts
Do not remove Karl Pond or Terra Dominguez from your LEA or schools
If these accounts are removed, the state cannot load your data
The state will load the data submitted by the LEAs, the state will not modify LEA data other than stated on slide 107
Originally Presented: 5/15/2015

## Slide 101: Federal Portal – Provisioning Accounts
Once data has been loaded by the state, LEAs may remove state access as deemed appropriate
OCR CRDC Federal Resources:
  How To Add New Users https://crdc.grads360.org/#communities/pdc/documents/7735
  How to Add Back SEA (state) Permissions https://crdc.grads360.org/#communities/pdc/documents/7734
Originally Presented: 5/15/2015

## Slide 102: State Data Load - LEA Action Required
LEAs must add Teacher Absenteeism to the Federal Submission Portal to complete the submission
Teacher Absenteeism is a school level data element
The NC DPI has all data elements for the CRDC collection with the exception of Teacher Absenteeism
Originally Presented: 5/15/2015

## Slide 103: State Data Load Status
Finance and Expenditure data come from LEA Monthly Financial Report (MFR) and Annual Financial Report (AFR)
Data will be loaded exactly as provided to the state
Originally Presented: 5/15/2015

## Slide 104: State Data Load Status
LEA and student level data from the PowerSchool CRDC reports may be transformed for the file submission
  Examples:
    LEA Level: number of schools on PowerSchool CRDC report may reflect Program /non-public schools. Count will be updated to reflect federally recognized public school count
    Grade 13 will be counted as grade 12
Originally Presented: 5/15/2015

## Slide 105: State Data Load Schedule
State will begin to load data the week of May 26, 2015
State hopes to conclude data submission June 5, 2015
LEA OCR Coordinators will be notified as each file submission is complete
Data will be submitted to the Federal Submission Portal in stages
Originally Presented: 5/15/2015

## Slide 106: State Data Load Schedule - Proposed
May 26, 2015 – Staff and Expenditure Data
May 28, 2015 – LEA Level Part 1 and Part 2
June 1, 2015 – School Level Part 1 and Part 2
Originally Presented: 5/15/2015

## Slide 107: June 19 - Agenda
State Data Load Status
  LEA / Charter Responsibilities
    Errors, Warnings and EDFacts
    Finance Data
    Teacher Absenteeism Data
    Certification
Support and Resources
Originally Presented: 6/19/2015

## Slide 108: State Data Load Schedule - Proposed
May 26, 2015 – Staff and Expenditure Data
  Completed May 26
May 28, 2015 – LEA Level Part 1 and Part 2
  Completed May 28
Week of June 1, 2015 – School Level Part 1 and Part 2
  Delayed one week, completed week of June 8
Originally Presented: 5/15/2015, updated 6/19/2015

## Slide 109: PowerSchool CRDC Report Status
All LEA level PowerSchool reports have been restored
All School level reports have been restored
Process to be run this weekend to Archive all reports at every level
Originally Presented 6/19/2015

## Slide 110: LEA / Charter Responsibilities
Create Federal Portal accounts
Review data submitted by the NC DPI
Update Teacher Absenteeism
Resolve all Errors
Review and document Warnings
Certify the Collection
Originally Presented: 5/15/2015

## Slide 111: Federal Portal – Provisioning Accounts
Provisioning accounts to the Federal Portal is at the discretion of the LEA. Some LEAs are:
  Provisioning accounts to all Principals
  Provisioning accounts to relevant business areas
    An example is staff in finance
  Allowing only those who certify data to access the Federal Portal
Originally Presented: 5/15/2015

## Slide 112: Sooo……What am I Doing?
OCR Contacts were provided user accounts to the Federal Submission Portal
  https://surveys.nces.ed.gov/CRDC/
  User name is your email address
  Forgot your password?
Click the Forgot your Password link.
The system will ask for your user name and send you the reset password
Originally Presented: 6/19/2015

## Slide 113: CRDC Submission Portal
First review your LEA for percentage complete, Errors and Warnings
Use the Certification link on the landing page
Originally Presented: 6/19/2015

## Slide 114
Originally Presented: 6/19/2015

## Slide 115: Error Resolution and Warnings
Errors in the Federal Portal must be resolved prior to Certification
  Example: Some LEAs/Charters did not fill out the CRDC PowerSchool Screens.
    This data must be added to the Federal Portal Manually
Warnings will not halt the Certification process
  Warnings may be reviewed and updated as needed
  Some elements with Warnings will allow staff to document the discrepancy
Originally Presented: 5/15/2015

## Slide 116: Errors for NC
Must be resolved prior to Certification
Error rates by district vary across state
Errors will provide guidance and elements effected if the Error Icon is clicked
LEAs may download the Error Resolution Report for the entire district
Originally Presented: 6/19/2015

## Slide 117: Warning Rates for NC
Do not require resolution prior to Certification
Some warnings provide a notes field
Are exceptionally high for NC school data
  All SY 13/14 elements, regardless of school type, were uploaded to the Federal Portal
    This means a 0 count was applied to an element if the school type did not collect the data. A large % of warnings are due to 0 counts.
    If you have reviewed your data and these fields should be inapplicable, then you do not need to do anything else. The fields will automatically be filled with "N/A" during certification
Warnings are now generated based on data submitted to EDFacts
Originally Presented: 6/19/2015

## Slide 118: EDFacts
EDFacts is a tool used by the State to submit the Federal reporting
  This year the Federal Portal will validate against previously submitted EDFacts reports
  In future submissions, if data has already been provided to the Federal Government, the data will be pre-populated into the Federal Submission Portal.
    This enhancement will continue to reduce the amount of time LEAs and Charters spend on the collection and review process prior to certification
Originally Presented: 5/15/2015

## Slide 119: Finance Data
Finance and Expenditure data come from LEA Monthly Financial Report (MFR) and Annual Financial Report (AFR)
Data will be loaded exactly as provided to the state
Please review the following sections in the Federal Submission tool carefully:
  STAF School & School Support Staff
  EXPD School Expenditures (Personnel and Non-Personnel)
Originally Presented: 6/19/2015

## Slide 120: Teacher Absenteeism
Manual update at school level
~OR~
Create a template:
  Column 1: SCH_ID
    Column 1 Format: Numeric
  Column 2: SCH_FTETEACH_ABSENT
    Column 2 Format: Numeric, 100th decimal
  File must be CSV
Originally Presented: 6/19/2015
Populate SCH_ID with your School’s Federal ID

## Slide 121: Federal IDs are in EDDIE
http://apps.schools.nc.gov/pls/apex/f?p=125:1:
Click Create Custom Report – School
Click All Schools/All Statuses/All Years
Click Actions
Click Select Columns
Originally Presented: 6/19/2015

## Slide 122: Selecting Elements in EDDIE...
Highlight all elements in Display in Report
Click the Double Chevron pointing left
Double click the following elements:
Originally Presented: 6/19/2015

## Slide 123: Select Elements in EDDIE...
Elements:
  School Number
  School Year
  Sch Operational Desc
  Opening Date
  Closing Date
  Federal School Number
Click Apply
Filter by School Year 2014
Originally Presented: 6/19/2015

## Slide 124: Download Federal IDs from Eddie
Click Actions
Click Download
Download as a .CSV file
Originally Presented: 6/19/2015

## Slide 125: Create Federal Upload File
Delete:
  Rows for schools not open during the SY 13/14 year
  All columns except Federal School Number
Update Federal School Number column header to SCH_ID
  Column 1 Format: Numeric
Update the second column header to SCH_FTETEACH_ABSENT
  Column 2 Format: Numeric, 100th decimal
Save as .CSV
Originally Presented: 6/19/2015

## Slide 126: Certification
Must be completed by August 7, 2015
Originally Presented: 6/19/2015

## Slide 127: Federal Portal – Familiarize Yourself
OCR CRDC Federal Resources:
  CRDC Survey Tool User Guide https://crdc.grads360.org/#communities/pdc/documents/7728
    Logging In and Home Page
    Reporting Data
    Resources Page (links in the Federal System)
    Reports (includes Submission Progress, Error Resolution, User Access, Collection Metrics)
    Certification
Originally Presented: 5/15/2015

## Slide 128: Support
Issue / Concern | Contact | Contact Info
No access to Federal Portal Incorrect permissions for account School does not exist in the Federal Portal | CRDC Partner Support | (844) 338-2732 or CRDC@SANAMETRIX.COM
Data not loaded for school Questions about data | HBSC Support Center | (919) 807-4357 or Homebase.incidents@its.nc.gov
Originally Presented: 5/15/2015

## Slide 129: Resources
Source | Document | Link
NC DPI | Preparing PowerSchool for the CRDC | http://www.nc-sis.org/Documents/school_info/OCR_v9_Final_20150313.pdf
Federal OCR | CRDC Survey Tool User Guide | https://crdc.grads360.org/#communities/pdc/documents/7728
Federal OCR | How to Add New Users | https://crdc.grads360.org/#communities/pdc/documents/7735
Federal OCR | How to Add Back SEA Permissions | https://crdc.grads360.org/#communities/pdc/documents/7734
Originally Presented: 5/15/2015
For all OCR Federal resources, visit: https://crdc.grads360.org/#program

## Slide 130: Resources
This presentation
  Collection of each status
  Evolution of processes
  Footers identify first and last update
    Some slides re-used and moved for flow
Communications Archive
  http://www.ncpublicschools.org/data/management/ocr/archive/
Originally Presented: 6/19/2015

## Slide 131: Thank You NC Public Schools!