Procurement Timeline: Contracting with a Food Service Management Company (FSMC)
	Due Date
	Action

	November 1
	Must notify the State Agency (SA) Procurement Specialist with your Intent to Procure a FSMC by November 1.

FSMC Request for Proposal (RFP) Template Available 
Contact State Agency Procurement Specialist for the Template


	December
	School Food Authority (SFA) Develops RFP for FSMC Solicitation 

	January 15
	Submit Draft RFP to State Agency (SA) for Review

	January 15 through February 15
	School Food Authority (SFA) Finalizes RFP 

	February 15
	Release FSMC RFP Solicitation

	March 15
	Vendor questions Due to SFA

	March 31
	Proposals Due to School Food Authority 

	April 1 through April 15
	Committee Evaluation and Scoring of Proposals
FSMC Presentations to the SFA


	April 20
	
Submit Evaluation Documentation to State Agency

	May 1
	Issue Notice of Intent to Award

	May 1 through May 10
	Vendor Protest Period

	May 15 through June 1
	Finalize Contract Language

	June 1
	Final Contract Due to State Agency

	July 1
	Execute Contract
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