Procurement Timeline: Contracting with a Food Service Management Company (FSMC)

| Due Date | Action |
| --- | --- |
| November 1 | Must notify the State Agency (SA) Procurement Specialist with your Intent to Procure a FSMC by November 1. FSMC Request for Proposal (RFP) Template Available Contact State Agency Procurement Specialist for the Template |
| December | School Food Authority (SFA) Develops RFP for FSMC Solicitation |
| January 15 | Submit Draft RFP to State Agency (SA) for Review |
| January 15 through February 15 | School Food Authority (SFA) Finalizes RFP |
| February 15 | Release FSMC RFP Solicitation |
| March 15 | Vendor questions Due to SFA |
| March 31 | Proposals Due to School Food Authority |
| April 1 through April 15 | Committee Evaluation and Scoring of Proposals FSMC Presentations to the SFA |
| April 20 | Submit Evaluation Documentation to State Agency |
| May 1 | Issue Notice of Intent to Award |
| May 1 through May 10 | Vendor Protest Period |
| May 15 through June 1 | Finalize Contract Language |
| June 1 | Final Contract Due to State Agency |
| July 1 | Execute Contract |